## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Tushar Kukreti | 2025-02-21 | Error with extraction via API | S2 | Tushar Kukreti | Bugs | Adhered to the bank policy and extraction documents | 2025-02-24 | Open | Require further investigation
2 | Tushar Kukreti | 2025-02-26 | Error with OCR text extraction accuracy | S3 | Tushar Kukreti | bugs | Adopted Pre-processing techniques | 29-Feb-2025 | Closed | Enhanced the accuarcy
3 | Tushar Kukreti | 2025-03-02 | Error with llm model fine-tuning | S6 | Tushar Kukreti | complexity | Utilized distilled versions for better performace | 2025-03-05 | Closed | Improved performance

## Sheet2
Logical
User Interface
Maintainability
Standards
Others